## Manpower Report by Task
PROGRESS REPORT PACKAGE
MANPOWER REPORT BY TASK
Select ONE:
FALSE | FALSE
FALSE | FALSE
VENDOR: | [6 empty] | PROGRESS REPORT NO.:
CONTRACT NO.: | [5 empty] | PERIOD: |  |  |  | THRU
|  | (From Exhibit A from your Tollway Task) |  | ACTUAL
(From Exhibit A from your Tollway Task)
|  | (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12)
TASKS (list Prime and Subconsultant tasks separately) |  | Total MH scheduled | Total MH scheduled to date | MH expended this period |  |  | Sum of all MH expended to date |  |  | % of Total scheduled MH to date | Estimate % of work completed to date | Estimate of additional MH required to complete Item | Grand Total of MH required to complete Item (Col 11+Col 8)
|  |  |  | Prime | Subs | Total | Prime | Subs | Total | (Col 8 / Col 2)
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 | 0 |  |  | 0
TOTALS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| NOTES: | (1): MH = Man-hours
|  | Column 10: | Vendor Project Manager must estimate the percent of work completed to date.
|  | Column 11: | Vendor Project Manager must estimate the total man-hours required to complete the specific item.
|  | Column 12: | If the total in Col. 12 exceeds the total in Col. 1, please attach a detailed explanation.
MONTHLY PROGRESS REPORT PACKAGE PAGE _____ OF ______
Note: Fields shaded in gray are automatically populated. Do not alter formulas.